## Overview
Power BI Corporate Training: 3-Tier Programme Tracker
Tier 1 Consumers ¦ Tier 2 Creators ¦ Tier 3 Builders. Each session is a 2-hour block, so the content can be delivered on any calendar pattern.
Programme progress by tier
Tier | Audience | Sessions | Planned Hrs | Completed | % Complete | Actual Hrs | Start Date | Last Session
Tier 1: Report Consumers | Managers, executives and business users who read and act on dashboards | 4 | 8 | 0 | 0% | 0 | 2026-09-21 | 2026-09-24
Tier 2: Report Creators | Business, finance and MIS analysts who build reports from existing or simple datasets | 12 | 24 | 0 | 0% | 0 | 2026-09-21 | 2026-10-06
Tier 3: Data & Model Builders | BI developers and reporting analysts who own and maintain datasets (PL-300 equivalent) | 30 | 60 | 0 | 0% | 0 | 2026-09-21 | 2026-10-30
Progress by module
Tier | Module | Sessions | Completed | % Complete | Planned Hrs | Actual Hrs
Tier 1: Report Consumers | 1. Power BI Foundations | 1 | 0 | 0% | 2 | 0
Tier 1: Report Consumers | 2. Explore & Interact with Reports | 2 | 0 | 0% | 4 | 0
Tier 1: Report Consumers | 3. Share & Stay Informed | 1 | 0 | 0% | 2 | 0
Tier 2: Report Creators | 1. Data Connect & Data Preparation | 3 | 0 | 0% | 6 | 0
Tier 2: Report Creators | 2. Data Model & DAX (Core) | 4 | 0 | 0% | 8 | 0
Tier 2: Report Creators | 3. Visualisations | 4 | 0 | 0% | 8 | 0
Tier 2: Report Creators | 4. Maintenance & Security (Essentials) | 1 | 0 | 0% | 2 | 0
Tier 3: Data & Model Builders | 1. Data Connect & Data Preparation | 7 | 0 | 0% | 14 | 0
Tier 3: Data & Model Builders | 2. Data Model & DAX | 9 | 0 | 0% | 18 | 0
Tier 3: Data & Model Builders | 3. Visualisations | 7 | 0 | 0% | 14 | 0
Tier 3: Data & Model Builders | 4. Maintenance & Security | 4 | 0 | 0% | 8 | 0
Tier 3: Data & Model Builders | 5. Mock Exams & Revision | 3 | 0 | 0% | 6 | 0
How to use this workbook
Yellow cells with blue text are yours to edit: start dates, training days and sessions per day on Schedule Planner; Status, Actual Hrs and Notes on each tier sheet; Date, Score and Max Score on Assessment Log. Everything else calculates.
Scheduling: the content is split into 2-hour sessions with no fixed calendar. On Schedule Planner, pick the start date, the weekdays the client can attend (1 or 0) and sessions per training day. For a Saturday and Sunday client, set Sat and Sun to 1 and use 2 sessions per day.
Set Status to Completed on a tier sheet and this Overview updates completion, hours and module progress automatically.
Pick the tier by role: see Tier Guide for audience, entry level, outcomes and example delivery patterns. The three tiers are independent, so a client can run just one or several.
Planned Hrs is 2 per session (editable on each tier sheet). Public holidays are not excluded from the calculated dates.

## Tier Guide
Tier Guide
Choose the tier by how each employee uses Power BI. Sessions and hours pull from the tier sheets.
Tier | Audience | Entry level | What they can do afterwards | Not covered | Sessions | Total Hrs | Example delivery
Tier 1: Report Consumers | Managers, executives and business users who read and act on dashboards | No Power BI experience needed; basic comfort with Excel helps | Navigate the Power BI Service, read visuals correctly, filter and drill into reports, export, subscribe and set alerts, and follow data-handling rules | Data preparation, data modelling, DAX and building reports | 4 | 8 | Two 4-hour training days (2 sessions per day), or 4 short evening sessions
Tier 2: Report Creators | Business, finance and MIS analysts who build reports from existing or simple datasets | Comfortable with Excel formulas and pivot tables; Tier 1 content or equivalent | Load and clean data, build a simple star-schema model, write core DAX measures including time intelligence basics, design interactive reports, publish and share through the Service | Advanced DAX and performance tuning, gateways, incremental refresh, implementing row-level security, deployment pipelines | 12 | 24 | 3 weekends with Saturday and Sunday at 2 sessions per day, or 3 weeks at 4 sessions per week
Tier 3: Data & Model Builders | BI developers and reporting analysts who own and maintain datasets (PL-300 equivalent) | Strong Excel and preferably SQL; Tier 2 skills or equivalent hands-on experience | PL-300-equivalent skills: full data preparation, modelling, advanced DAX, performance tuning, visualisation and AI features, workspace administration, refresh and gateways, row-level and object-level security | Fabric-specific engineering (lakehouses, pipelines) and Power BI admin-portal tenant settings | 30 | 60 | Around 6 weeks at 5 sessions per week, or 8 weekends at 4 sessions per weekend. Sessions 28-30 (mock exams) are optional for clients not seeking certification
Tier 3 module weights follow Microsoft's PL-300 skills measured (roughly 25-30% each for prepare, model and visualise; 15-20% for manage and secure). Check the current study guide, as objectives are updated from time to time.

## Schedule Planner
Schedule Planner
Set the training days for each tier. Session dates on the tier sheets calculate from these inputs. Nothing here assumes weekdays.
[8 empty] | Helper calendar: Tier 1: Report Consumers (do not edit) |  |  | Helper calendar: Tier 2: Report Creators (do not edit) |  |  | Helper calendar: Tier 3: Data & Model Builders (do not edit)
Tier 1: Report Consumers | [7 empty] | Date | Held? | Cumulative | Date | Held? | Cumulative | Date | Held? | Cumulative
Start date | 2026-09-21 | <- placeholder, edit | [5 empty] | 2026-09-21 | 1 | 1 | 2026-09-21 | 1 | 1 | 2026-09-21 | 1 | 1
Training day | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026-09-22 | 1 | 2 | 2026-09-22 | 1 | 2 | 2026-09-22 | 1 | 2
Held on this day? (1 = yes, 0 = no) | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2026-09-23 | 1 | 3 | 2026-09-23 | 1 | 3 | 2026-09-23 | 1 | 3
Sessions per training day (1 session = 2 hrs) | 1 | [6 empty] | 2026-09-24 | 1 | 4 | 2026-09-24 | 1 | 4 | 2026-09-24 | 1 | 4
Total sessions | 4 | [6 empty] | 2026-09-25 | 1 | 5 | 2026-09-25 | 1 | 5 | 2026-09-25 | 1 | 5
Training days needed | 4 | [6 empty] | 2026-09-26 | 0 | 5 | 2026-09-26 | 0 | 5 | 2026-09-26 | 0 | 5
Last session date | 2026-09-24 | [6 empty] | 2026-09-27 | 0 | 5 | 2026-09-27 | 0 | 5 | 2026-09-27 | 0 | 5
[8 empty] | 2026-09-28 | 1 | 6 | 2026-09-28 | 1 | 6 | 2026-09-28 | 1 | 6
[8 empty] | 2026-09-29 | 1 | 7 | 2026-09-29 | 1 | 7 | 2026-09-29 | 1 | 7
Tier 2: Report Creators | [7 empty] | 2026-09-30 | 1 | 8 | 2026-09-30 | 1 | 8 | 2026-09-30 | 1 | 8
Start date | 2026-09-21 | <- placeholder, edit | [5 empty] | 2026-10-01 | 1 | 9 | 2026-10-01 | 1 | 9 | 2026-10-01 | 1 | 9
Training day | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026-10-02 | 1 | 10 | 2026-10-02 | 1 | 10 | 2026-10-02 | 1 | 10
Held on this day? (1 = yes, 0 = no) | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2026-10-03 | 0 | 10 | 2026-10-03 | 0 | 10 | 2026-10-03 | 0 | 10
Sessions per training day (1 session = 2 hrs) | 1 | [6 empty] | 2026-10-04 | 0 | 10 | 2026-10-04 | 0 | 10 | 2026-10-04 | 0 | 10
Total sessions | 12 | [6 empty] | 2026-10-05 | 1 | 11 | 2026-10-05 | 1 | 11 | 2026-10-05 | 1 | 11
Training days needed | 12 | [6 empty] | 2026-10-06 | 1 | 12 | 2026-10-06 | 1 | 12 | 2026-10-06 | 1 | 12
Last session date | 2026-10-06 | [6 empty] | 2026-10-07 | 1 | 13 | 2026-10-07 | 1 | 13 | 2026-10-07 | 1 | 13
[8 empty] | 2026-10-08 | 1 | 14 | 2026-10-08 | 1 | 14 | 2026-10-08 | 1 | 14
[8 empty] | 2026-10-09 | 1 | 15 | 2026-10-09 | 1 | 15 | 2026-10-09 | 1 | 15
Tier 3: Data & Model Builders | [7 empty] | 2026-10-10 | 0 | 15 | 2026-10-10 | 0 | 15 | 2026-10-10 | 0 | 15
Start date | 2026-09-21 | <- placeholder, edit | [5 empty] | 2026-10-11 | 0 | 15 | 2026-10-11 | 0 | 15 | 2026-10-11 | 0 | 15
Training day | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026-10-12 | 1 | 16 | 2026-10-12 | 1 | 16 | 2026-10-12 | 1 | 16
Held on this day? (1 = yes, 0 = no) | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2026-10-13 | 1 | 17 | 2026-10-13 | 1 | 17 | 2026-10-13 | 1 | 17
Sessions per training day (1 session = 2 hrs) | 1 | [6 empty] | 2026-10-14 | 1 | 18 | 2026-10-14 | 1 | 18 | 2026-10-14 | 1 | 18
Total sessions | 30 | [6 empty] | 2026-10-15 | 1 | 19 | 2026-10-15 | 1 | 19 | 2026-10-15 | 1 | 19
Training days needed | 30 | [6 empty] | 2026-10-16 | 1 | 20 | 2026-10-16 | 1 | 20 | 2026-10-16 | 1 | 20
Last session date | 2026-10-30 | [6 empty] | 2026-10-17 | 0 | 20 | 2026-10-17 | 0 | 20 | 2026-10-17 | 0 | 20
[8 empty] | 2026-10-18 | 0 | 20 | 2026-10-18 | 0 | 20 | 2026-10-18 | 0 | 20
[8 empty] | 2026-10-19 | 1 | 21 | 2026-10-19 | 1 | 21 | 2026-10-19 | 1 | 21
[8 empty] | 2026-10-20 | 1 | 22 | 2026-10-20 | 1 | 22 | 2026-10-20 | 1 | 22
How to use: set the Start date, mark the weekdays the client can attend with 1 (others 0), and choose sessions per training day. Every session is a 2-hour block. | [7 empty] | 2026-10-21 | 1 | 23 | 2026-10-21 | 1 | 23 | 2026-10-21 | 1 | 23
Weekend-only client: set Sat = 1 and Sun = 1, all other days = 0. With 2 sessions per training day each Saturday and Sunday is a 4-hour day, so Tier 2 (12 sessions) finishes in 3 weekends. | [7 empty] | 2026-10-22 | 1 | 24 | 2026-10-22 | 1 | 24 | 2026-10-22 | 1 | 24
Any other pattern works the same way (for example Tue/Thu evenings with 1 session per day). Defaults are Mon-Fri with 1 session per day, only as a starting point. | [7 empty] | 2026-10-23 | 1 | 25 | 2026-10-23 | 1 | 25 | 2026-10-23 | 1 | 25
Helper calendar columns K:S are hidden and drive the dates. Public holidays are not excluded; shift the dates on the tier sheet manually if needed. | [7 empty] | 2026-10-24 | 0 | 25 | 2026-10-24 | 0 | 25 | 2026-10-24 | 0 | 25
[8 empty] | 2026-10-25 | 0 | 25 | 2026-10-25 | 0 | 25 | 2026-10-25 | 0 | 25
[8 empty] | 2026-10-26 | 1 | 26 | 2026-10-26 | 1 | 26 | 2026-10-26 | 1 | 26
[8 empty] | 2026-10-27 | 1 | 27 | 2026-10-27 | 1 | 27 | 2026-10-27 | 1 | 27
[8 empty] | 2026-10-28 | 1 | 28 | 2026-10-28 | 1 | 28 | 2026-10-28 | 1 | 28
[8 empty] | 2026-10-29 | 1 | 29 | 2026-10-29 | 1 | 29 | 2026-10-29 | 1 | 29
[8 empty] | 2026-10-30 | 1 | 30 | 2026-10-30 | 1 | 30 | 2026-10-30 | 1 | 30
[8 empty] | 2026-10-31 | 0 | 30 | 2026-10-31 | 0 | 30 | 2026-10-31 | 0 | 30
[8 empty] | 2026-11-01 | 0 | 30 | 2026-11-01 | 0 | 30 | 2026-11-01 | 0 | 30
[8 empty] | 2026-11-02 | 1 | 31 | 2026-11-02 | 1 | 31 | 2026-11-02 | 1 | 31
[8 empty] | 2026-11-03 | 1 | 32 | 2026-11-03 | 1 | 32 | 2026-11-03 | 1 | 32
[8 empty] | 2026-11-04 | 1 | 33 | 2026-11-04 | 1 | 33 | 2026-11-04 | 1 | 33
[8 empty] | 2026-11-05 | 1 | 34 | 2026-11-05 | 1 | 34 | 2026-11-05 | 1 | 34
[8 empty] | 2026-11-06 | 1 | 35 | 2026-11-06 | 1 | 35 | 2026-11-06 | 1 | 35
[8 empty] | 2026-11-07 | 0 | 35 | 2026-11-07 | 0 | 35 | 2026-11-07 | 0 | 35
[8 empty] | 2026-11-08 | 0 | 35 | 2026-11-08 | 0 | 35 | 2026-11-08 | 0 | 35
[8 empty] | 2026-11-09 | 1 | 36 | 2026-11-09 | 1 | 36 | 2026-11-09 | 1 | 36
[8 empty] | 2026-11-10 | 1 | 37 | 2026-11-10 | 1 | 37 | 2026-11-10 | 1 | 37
[8 empty] | 2026-11-11 | 1 | 38 | 2026-11-11 | 1 | 38 | 2026-11-11 | 1 | 38
[8 empty] | 2026-11-12 | 1 | 39 | 2026-11-12 | 1 | 39 | 2026-11-12 | 1 | 39
[8 empty] | 2026-11-13 | 1 | 40 | 2026-11-13 | 1 | 40 | 2026-11-13 | 1 | 40
[8 empty] | 2026-11-14 | 0 | 40 | 2026-11-14 | 0 | 40 | 2026-11-14 | 0 | 40
[8 empty] | 2026-11-15 | 0 | 40 | 2026-11-15 | 0 | 40 | 2026-11-15 | 0 | 40
[8 empty] | 2026-11-16 | 1 | 41 | 2026-11-16 | 1 | 41 | 2026-11-16 | 1 | 41
[8 empty] | 2026-11-17 | 1 | 42 | 2026-11-17 | 1 | 42 | 2026-11-17 | 1 | 42
[8 empty] | 2026-11-18 | 1 | 43 | 2026-11-18 | 1 | 43 | 2026-11-18 | 1 | 43
[8 empty] | 2026-11-19 | 1 | 44 | 2026-11-19 | 1 | 44 | 2026-11-19 | 1 | 44
[8 empty] | 2026-11-20 | 1 | 45 | 2026-11-20 | 1 | 45 | 2026-11-20 | 1 | 45
[8 empty] | 2026-11-21 | 0 | 45 | 2026-11-21 | 0 | 45 | 2026-11-21 | 0 | 45
[8 empty] | 2026-11-22 | 0 | 45 | 2026-11-22 | 0 | 45 | 2026-11-22 | 0 | 45
[8 empty] | 2026-11-23 | 1 | 46 | 2026-11-23 | 1 | 46 | 2026-11-23 | 1 | 46
[8 empty] | 2026-11-24 | 1 | 47 | 2026-11-24 | 1 | 47 | 2026-11-24 | 1 | 47
[8 empty] | 2026-11-25 | 1 | 48 | 2026-11-25 | 1 | 48 | 2026-11-25 | 1 | 48
[8 empty] | 2026-11-26 | 1 | 49 | 2026-11-26 | 1 | 49 | 2026-11-26 | 1 | 49
[8 empty] | 2026-11-27 | 1 | 50 | 2026-11-27 | 1 | 50 | 2026-11-27 | 1 | 50
[8 empty] | 2026-11-28 | 0 | 50 | 2026-11-28 | 0 | 50 | 2026-11-28 | 0 | 50
[8 empty] | 2026-11-29 | 0 | 50 | 2026-11-29 | 0 | 50 | 2026-11-29 | 0 | 50
[8 empty] | 2026-11-30 | 1 | 51 | 2026-11-30 | 1 | 51 | 2026-11-30 | 1 | 51
[8 empty] | 2026-12-01 | 1 | 52 | 2026-12-01 | 1 | 52 | 2026-12-01 | 1 | 52
[8 empty] | 2026-12-02 | 1 | 53 | 2026-12-02 | 1 | 53 | 2026-12-02 | 1 | 53
[8 empty] | 2026-12-03 | 1 | 54 | 2026-12-03 | 1 | 54 | 2026-12-03 | 1 | 54
[8 empty] | 2026-12-04 | 1 | 55 | 2026-12-04 | 1 | 55 | 2026-12-04 | 1 | 55
[8 empty] | 2026-12-05 | 0 | 55 | 2026-12-05 | 0 | 55 | 2026-12-05 | 0 | 55
[8 empty] | 2026-12-06 | 0 | 55 | 2026-12-06 | 0 | 55 | 2026-12-06 | 0 | 55
[8 empty] | 2026-12-07 | 1 | 56 | 2026-12-07 | 1 | 56 | 2026-12-07 | 1 | 56
[8 empty] | 2026-12-08 | 1 | 57 | 2026-12-08 | 1 | 57 | 2026-12-08 | 1 | 57
[8 empty] | 2026-12-09 | 1 | 58 | 2026-12-09 | 1 | 58 | 2026-12-09 | 1 | 58
[8 empty] | 2026-12-10 | 1 | 59 | 2026-12-10 | 1 | 59 | 2026-12-10 | 1 | 59
[8 empty] | 2026-12-11 | 1 | 60 | 2026-12-11 | 1 | 60 | 2026-12-11 | 1 | 60
[8 empty] | 2026-12-12 | 0 | 60 | 2026-12-12 | 0 | 60 | 2026-12-12 | 0 | 60
[8 empty] | 2026-12-13 | 0 | 60 | 2026-12-13 | 0 | 60 | 2026-12-13 | 0 | 60
[8 empty] | 2026-12-14 | 1 | 61 | 2026-12-14 | 1 | 61 | 2026-12-14 | 1 | 61
[8 empty] | 2026-12-15 | 1 | 62 | 2026-12-15 | 1 | 62 | 2026-12-15 | 1 | 62
[8 empty] | 2026-12-16 | 1 | 63 | 2026-12-16 | 1 | 63 | 2026-12-16 | 1 | 63
[8 empty] | 2026-12-17 | 1 | 64 | 2026-12-17 | 1 | 64 | 2026-12-17 | 1 | 64
[8 empty] | 2026-12-18 | 1 | 65 | 2026-12-18 | 1 | 65 | 2026-12-18 | 1 | 65
[8 empty] | 2026-12-19 | 0 | 65 | 2026-12-19 | 0 | 65 | 2026-12-19 | 0 | 65
[8 empty] | 2026-12-20 | 0 | 65 | 2026-12-20 | 0 | 65 | 2026-12-20 | 0 | 65
[8 empty] | 2026-12-21 | 1 | 66 | 2026-12-21 | 1 | 66 | 2026-12-21 | 1 | 66
[8 empty] | 2026-12-22 | 1 | 67 | 2026-12-22 | 1 | 67 | 2026-12-22 | 1 | 67
[8 empty] | 2026-12-23 | 1 | 68 | 2026-12-23 | 1 | 68 | 2026-12-23 | 1 | 68
[8 empty] | 2026-12-24 | 1 | 69 | 2026-12-24 | 1 | 69 | 2026-12-24 | 1 | 69
[8 empty] | 2026-12-25 | 1 | 70 | 2026-12-25 | 1 | 70 | 2026-12-25 | 1 | 70
[8 empty] | 2026-12-26 | 0 | 70 | 2026-12-26 | 0 | 70 | 2026-12-26 | 0 | 70
[8 empty] | 2026-12-27 | 0 | 70 | 2026-12-27 | 0 | 70 | 2026-12-27 | 0 | 70
[8 empty] | 2026-12-28 | 1 | 71 | 2026-12-28 | 1 | 71 | 2026-12-28 | 1 | 71
[8 empty] | 2026-12-29 | 1 | 72 | 2026-12-29 | 1 | 72 | 2026-12-29 | 1 | 72
[8 empty] | 2026-12-30 | 1 | 73 | 2026-12-30 | 1 | 73 | 2026-12-30 | 1 | 73
[8 empty] | 2026-12-31 | 1 | 74 | 2026-12-31 | 1 | 74 | 2026-12-31 | 1 | 74
[8 empty] | 2027-01-01 | 1 | 75 | 2027-01-01 | 1 | 75 | 2027-01-01 | 1 | 75
[8 empty] | 2027-01-02 | 0 | 75 | 2027-01-02 | 0 | 75 | 2027-01-02 | 0 | 75
[8 empty] | 2027-01-03 | 0 | 75 | 2027-01-03 | 0 | 75 | 2027-01-03 | 0 | 75
[8 empty] | 2027-01-04 | 1 | 76 | 2027-01-04 | 1 | 76 | 2027-01-04 | 1 | 76
[8 empty] | 2027-01-05 | 1 | 77 | 2027-01-05 | 1 | 77 | 2027-01-05 | 1 | 77
[8 empty] | 2027-01-06 | 1 | 78 | 2027-01-06 | 1 | 78 | 2027-01-06 | 1 | 78
[8 empty] | 2027-01-07 | 1 | 79 | 2027-01-07 | 1 | 79 | 2027-01-07 | 1 | 79
[8 empty] | 2027-01-08 | 1 | 80 | 2027-01-08 | 1 | 80 | 2027-01-08 | 1 | 80
[8 empty] | 2027-01-09 | 0 | 80 | 2027-01-09 | 0 | 80 | 2027-01-09 | 0 | 80
[8 empty] | 2027-01-10 | 0 | 80 | 2027-01-10 | 0 | 80 | 2027-01-10 | 0 | 80
[8 empty] | 2027-01-11 | 1 | 81 | 2027-01-11 | 1 | 81 | 2027-01-11 | 1 | 81
[8 empty] | 2027-01-12 | 1 | 82 | 2027-01-12 | 1 | 82 | 2027-01-12 | 1 | 82
[8 empty] | 2027-01-13 | 1 | 83 | 2027-01-13 | 1 | 83 | 2027-01-13 | 1 | 83
[8 empty] | 2027-01-14 | 1 | 84 | 2027-01-14 | 1 | 84 | 2027-01-14 | 1 | 84
[8 empty] | 2027-01-15 | 1 | 85 | 2027-01-15 | 1 | 85 | 2027-01-15 | 1 | 85
[8 empty] | 2027-01-16 | 0 | 85 | 2027-01-16 | 0 | 85 | 2027-01-16 | 0 | 85
[8 empty] | 2027-01-17 | 0 | 85 | 2027-01-17 | 0 | 85 | 2027-01-17 | 0 | 85
[8 empty] | 2027-01-18 | 1 | 86 | 2027-01-18 | 1 | 86 | 2027-01-18 | 1 | 86
[8 empty] | 2027-01-19 | 1 | 87 | 2027-01-19 | 1 | 87 | 2027-01-19 | 1 | 87
[8 empty] | 2027-01-20 | 1 | 88 | 2027-01-20 | 1 | 88 | 2027-01-20 | 1 | 88
[8 empty] | 2027-01-21 | 1 | 89 | 2027-01-21 | 1 | 89 | 2027-01-21 | 1 | 89
[8 empty] | 2027-01-22 | 1 | 90 | 2027-01-22 | 1 | 90 | 2027-01-22 | 1 | 90
[8 empty] | 2027-01-23 | 0 | 90 | 2027-01-23 | 0 | 90 | 2027-01-23 | 0 | 90
[8 empty] | 2027-01-24 | 0 | 90 | 2027-01-24 | 0 | 90 | 2027-01-24 | 0 | 90
[8 empty] | 2027-01-25 | 1 | 91 | 2027-01-25 | 1 | 91 | 2027-01-25 | 1 | 91
[8 empty] | 2027-01-26 | 1 | 92 | 2027-01-26 | 1 | 92 | 2027-01-26 | 1 | 92
[8 empty] | 2027-01-27 | 1 | 93 | 2027-01-27 | 1 | 93 | 2027-01-27 | 1 | 93
[8 empty] | 2027-01-28 | 1 | 94 | 2027-01-28 | 1 | 94 | 2027-01-28 | 1 | 94
[8 empty] | 2027-01-29 | 1 | 95 | 2027-01-29 | 1 | 95 | 2027-01-29 | 1 | 95
[8 empty] | 2027-01-30 | 0 | 95 | 2027-01-30 | 0 | 95 | 2027-01-30 | 0 | 95
[8 empty] | 2027-01-31 | 0 | 95 | 2027-01-31 | 0 | 95 | 2027-01-31 | 0 | 95
[8 empty] | 2027-02-01 | 1 | 96 | 2027-02-01 | 1 | 96 | 2027-02-01 | 1 | 96
[8 empty] | 2027-02-02 | 1 | 97 | 2027-02-02 | 1 | 97 | 2027-02-02 | 1 | 97
[8 empty] | 2027-02-03 | 1 | 98 | 2027-02-03 | 1 | 98 | 2027-02-03 | 1 | 98
[8 empty] | 2027-02-04 | 1 | 99 | 2027-02-04 | 1 | 99 | 2027-02-04 | 1 | 99
[8 empty] | 2027-02-05 | 1 | 100 | 2027-02-05 | 1 | 100 | 2027-02-05 | 1 | 100
[8 empty] | 2027-02-06 | 0 | 100 | 2027-02-06 | 0 | 100 | 2027-02-06 | 0 | 100
[8 empty] | 2027-02-07 | 0 | 100 | 2027-02-07 | 0 | 100 | 2027-02-07 | 0 | 100
[8 empty] | 2027-02-08 | 1 | 101 | 2027-02-08 | 1 | 101 | 2027-02-08 | 1 | 101
[8 empty] | 2027-02-09 | 1 | 102 | 2027-02-09 | 1 | 102 | 2027-02-09 | 1 | 102
[8 empty] | 2027-02-10 | 1 | 103 | 2027-02-10 | 1 | 103 | 2027-02-10 | 1 | 103
[8 empty] | 2027-02-11 | 1 | 104 | 2027-02-11 | 1 | 104 | 2027-02-11 | 1 | 104
[8 empty] | 2027-02-12 | 1 | 105 | 2027-02-12 | 1 | 105 | 2027-02-12 | 1 | 105
[8 empty] | 2027-02-13 | 0 | 105 | 2027-02-13 | 0 | 105 | 2027-02-13 | 0 | 105
[8 empty] | 2027-02-14 | 0 | 105 | 2027-02-14 | 0 | 105 | 2027-02-14 | 0 | 105
[8 empty] | 2027-02-15 | 1 | 106 | 2027-02-15 | 1 | 106 | 2027-02-15 | 1 | 106
[8 empty] | 2027-02-16 | 1 | 107 | 2027-02-16 | 1 | 107 | 2027-02-16 | 1 | 107
[8 empty] | 2027-02-17 | 1 | 108 | 2027-02-17 | 1 | 108 | 2027-02-17 | 1 | 108
[8 empty] | 2027-02-18 | 1 | 109 | 2027-02-18 | 1 | 109 | 2027-02-18 | 1 | 109
[8 empty] | 2027-02-19 | 1 | 110 | 2027-02-19 | 1 | 110 | 2027-02-19 | 1 | 110
[8 empty] | 2027-02-20 | 0 | 110 | 2027-02-20 | 0 | 110 | 2027-02-20 | 0 | 110
[8 empty] | 2027-02-21 | 0 | 110 | 2027-02-21 | 0 | 110 | 2027-02-21 | 0 | 110
[8 empty] | 2027-02-22 | 1 | 111 | 2027-02-22 | 1 | 111 | 2027-02-22 | 1 | 111
[8 empty] | 2027-02-23 | 1 | 112 | 2027-02-23 | 1 | 112 | 2027-02-23 | 1 | 112
[8 empty] | 2027-02-24 | 1 | 113 | 2027-02-24 | 1 | 113 | 2027-02-24 | 1 | 113
[8 empty] | 2027-02-25 | 1 | 114 | 2027-02-25 | 1 | 114 | 2027-02-25 | 1 | 114
[8 empty] | 2027-02-26 | 1 | 115 | 2027-02-26 | 1 | 115 | 2027-02-26 | 1 | 115
[8 empty] | 2027-02-27 | 0 | 115 | 2027-02-27 | 0 | 115 | 2027-02-27 | 0 | 115
[8 empty] | 2027-02-28 | 0 | 115 | 2027-02-28 | 0 | 115 | 2027-02-28 | 0 | 115
[8 empty] | 2027-03-01 | 1 | 116 | 2027-03-01 | 1 | 116 | 2027-03-01 | 1 | 116
[8 empty] | 2027-03-02 | 1 | 117 | 2027-03-02 | 1 | 117 | 2027-03-02 | 1 | 117
[8 empty] | 2027-03-03 | 1 | 118 | 2027-03-03 | 1 | 118 | 2027-03-03 | 1 | 118
[8 empty] | 2027-03-04 | 1 | 119 | 2027-03-04 | 1 | 119 | 2027-03-04 | 1 | 119
[8 empty] | 2027-03-05 | 1 | 120 | 2027-03-05 | 1 | 120 | 2027-03-05 | 1 | 120
[8 empty] | 2027-03-06 | 0 | 120 | 2027-03-06 | 0 | 120 | 2027-03-06 | 0 | 120
[8 empty] | 2027-03-07 | 0 | 120 | 2027-03-07 | 0 | 120 | 2027-03-07 | 0 | 120
[8 empty] | 2027-03-08 | 1 | 121 | 2027-03-08 | 1 | 121 | 2027-03-08 | 1 | 121
[8 empty] | 2027-03-09 | 1 | 122 | 2027-03-09 | 1 | 122 | 2027-03-09 | 1 | 122
[8 empty] | 2027-03-10 | 1 | 123 | 2027-03-10 | 1 | 123 | 2027-03-10 | 1 | 123
[8 empty] | 2027-03-11 | 1 | 124 | 2027-03-11 | 1 | 124 | 2027-03-11 | 1 | 124
[8 empty] | 2027-03-12 | 1 | 125 | 2027-03-12 | 1 | 125 | 2027-03-12 | 1 | 125
[8 empty] | 2027-03-13 | 0 | 125 | 2027-03-13 | 0 | 125 | 2027-03-13 | 0 | 125
[8 empty] | 2027-03-14 | 0 | 125 | 2027-03-14 | 0 | 125 | 2027-03-14 | 0 | 125
[8 empty] | 2027-03-15 | 1 | 126 | 2027-03-15 | 1 | 126 | 2027-03-15 | 1 | 126
[8 empty] | 2027-03-16 | 1 | 127 | 2027-03-16 | 1 | 127 | 2027-03-16 | 1 | 127
[8 empty] | 2027-03-17 | 1 | 128 | 2027-03-17 | 1 | 128 | 2027-03-17 | 1 | 128
[8 empty] | 2027-03-18 | 1 | 129 | 2027-03-18 | 1 | 129 | 2027-03-18 | 1 | 129
[8 empty] | 2027-03-19 | 1 | 130 | 2027-03-19 | 1 | 130 | 2027-03-19 | 1 | 130
[8 empty] | 2027-03-20 | 0 | 130 | 2027-03-20 | 0 | 130 | 2027-03-20 | 0 | 130
[8 empty] | 2027-03-21 | 0 | 130 | 2027-03-21 | 0 | 130 | 2027-03-21 | 0 | 130
[8 empty] | 2027-03-22 | 1 | 131 | 2027-03-22 | 1 | 131 | 2027-03-22 | 1 | 131
[8 empty] | 2027-03-23 | 1 | 132 | 2027-03-23 | 1 | 132 | 2027-03-23 | 1 | 132
[8 empty] | 2027-03-24 | 1 | 133 | 2027-03-24 | 1 | 133 | 2027-03-24 | 1 | 133
[8 empty] | 2027-03-25 | 1 | 134 | 2027-03-25 | 1 | 134 | 2027-03-25 | 1 | 134
[8 empty] | 2027-03-26 | 1 | 135 | 2027-03-26 | 1 | 135 | 2027-03-26 | 1 | 135
[8 empty] | 2027-03-27 | 0 | 135 | 2027-03-27 | 0 | 135 | 2027-03-27 | 0 | 135
[8 empty] | 2027-03-28 | 0 | 135 | 2027-03-28 | 0 | 135 | 2027-03-28 | 0 | 135
[8 empty] | 2027-03-29 | 1 | 136 | 2027-03-29 | 1 | 136 | 2027-03-29 | 1 | 136
[8 empty] | 2027-03-30 | 1 | 137 | 2027-03-30 | 1 | 137 | 2027-03-30 | 1 | 137
[8 empty] | 2027-03-31 | 1 | 138 | 2027-03-31 | 1 | 138 | 2027-03-31 | 1 | 138
[8 empty] | 2027-04-01 | 1 | 139 | 2027-04-01 | 1 | 139 | 2027-04-01 | 1 | 139
[8 empty] | 2027-04-02 | 1 | 140 | 2027-04-02 | 1 | 140 | 2027-04-02 | 1 | 140
[8 empty] | 2027-04-03 | 0 | 140 | 2027-04-03 | 0 | 140 | 2027-04-03 | 0 | 140
[8 empty] | 2027-04-04 | 0 | 140 | 2027-04-04 | 0 | 140 | 2027-04-04 | 0 | 140
[8 empty] | 2027-04-05 | 1 | 141 | 2027-04-05 | 1 | 141 | 2027-04-05 | 1 | 141
[8 empty] | 2027-04-06 | 1 | 142 | 2027-04-06 | 1 | 142 | 2027-04-06 | 1 | 142
[8 empty] | 2027-04-07 | 1 | 143 | 2027-04-07 | 1 | 143 | 2027-04-07 | 1 | 143
[8 empty] | 2027-04-08 | 1 | 144 | 2027-04-08 | 1 | 144 | 2027-04-08 | 1 | 144
[8 empty] | 2027-04-09 | 1 | 145 | 2027-04-09 | 1 | 145 | 2027-04-09 | 1 | 145
[8 empty] | 2027-04-10 | 0 | 145 | 2027-04-10 | 0 | 145 | 2027-04-10 | 0 | 145
[8 empty] | 2027-04-11 | 0 | 145 | 2027-04-11 | 0 | 145 | 2027-04-11 | 0 | 145
[8 empty] | 2027-04-12 | 1 | 146 | 2027-04-12 | 1 | 146 | 2027-04-12 | 1 | 146
[8 empty] | 2027-04-13 | 1 | 147 | 2027-04-13 | 1 | 147 | 2027-04-13 | 1 | 147
[8 empty] | 2027-04-14 | 1 | 148 | 2027-04-14 | 1 | 148 | 2027-04-14 | 1 | 148
[8 empty] | 2027-04-15 | 1 | 149 | 2027-04-15 | 1 | 149 | 2027-04-15 | 1 | 149
[8 empty] | 2027-04-16 | 1 | 150 | 2027-04-16 | 1 | 150 | 2027-04-16 | 1 | 150
[8 empty] | 2027-04-17 | 0 | 150 | 2027-04-17 | 0 | 150 | 2027-04-17 | 0 | 150
[8 empty] | 2027-04-18 | 0 | 150 | 2027-04-18 | 0 | 150 | 2027-04-18 | 0 | 150
[8 empty] | 2027-04-19 | 1 | 151 | 2027-04-19 | 1 | 151 | 2027-04-19 | 1 | 151
[8 empty] | 2027-04-20 | 1 | 152 | 2027-04-20 | 1 | 152 | 2027-04-20 | 1 | 152
[8 empty] | 2027-04-21 | 1 | 153 | 2027-04-21 | 1 | 153 | 2027-04-21 | 1 | 153
[8 empty] | 2027-04-22 | 1 | 154 | 2027-04-22 | 1 | 154 | 2027-04-22 | 1 | 154
[8 empty] | 2027-04-23 | 1 | 155 | 2027-04-23 | 1 | 155 | 2027-04-23 | 1 | 155
[8 empty] | 2027-04-24 | 0 | 155 | 2027-04-24 | 0 | 155 | 2027-04-24 | 0 | 155
[8 empty] | 2027-04-25 | 0 | 155 | 2027-04-25 | 0 | 155 | 2027-04-25 | 0 | 155
[8 empty] | 2027-04-26 | 1 | 156 | 2027-04-26 | 1 | 156 | 2027-04-26 | 1 | 156
[8 empty] | 2027-04-27 | 1 | 157 | 2027-04-27 | 1 | 157 | 2027-04-27 | 1 | 157
[8 empty] | 2027-04-28 | 1 | 158 | 2027-04-28 | 1 | 158 | 2027-04-28 | 1 | 158
[8 empty] | 2027-04-29 | 1 | 159 | 2027-04-29 | 1 | 159 | 2027-04-29 | 1 | 159
[8 empty] | 2027-04-30 | 1 | 160 | 2027-04-30 | 1 | 160 | 2027-04-30 | 1 | 160
[8 empty] | 2027-05-01 | 0 | 160 | 2027-05-01 | 0 | 160 | 2027-05-01 | 0 | 160
[8 empty] | 2027-05-02 | 0 | 160 | 2027-05-02 | 0 | 160 | 2027-05-02 | 0 | 160
[8 empty] | 2027-05-03 | 1 | 161 | 2027-05-03 | 1 | 161 | 2027-05-03 | 1 | 161
[8 empty] | 2027-05-04 | 1 | 162 | 2027-05-04 | 1 | 162 | 2027-05-04 | 1 | 162
[8 empty] | 2027-05-05 | 1 | 163 | 2027-05-05 | 1 | 163 | 2027-05-05 | 1 | 163
[8 empty] | 2027-05-06 | 1 | 164 | 2027-05-06 | 1 | 164 | 2027-05-06 | 1 | 164
[8 empty] | 2027-05-07 | 1 | 165 | 2027-05-07 | 1 | 165 | 2027-05-07 | 1 | 165
[8 empty] | 2027-05-08 | 0 | 165 | 2027-05-08 | 0 | 165 | 2027-05-08 | 0 | 165
[8 empty] | 2027-05-09 | 0 | 165 | 2027-05-09 | 0 | 165 | 2027-05-09 | 0 | 165
[8 empty] | 2027-05-10 | 1 | 166 | 2027-05-10 | 1 | 166 | 2027-05-10 | 1 | 166
[8 empty] | 2027-05-11 | 1 | 167 | 2027-05-11 | 1 | 167 | 2027-05-11 | 1 | 167
[8 empty] | 2027-05-12 | 1 | 168 | 2027-05-12 | 1 | 168 | 2027-05-12 | 1 | 168
[8 empty] | 2027-05-13 | 1 | 169 | 2027-05-13 | 1 | 169 | 2027-05-13 | 1 | 169
[8 empty] | 2027-05-14 | 1 | 170 | 2027-05-14 | 1 | 170 | 2027-05-14 | 1 | 170
[8 empty] | 2027-05-15 | 0 | 170 | 2027-05-15 | 0 | 170 | 2027-05-15 | 0 | 170
[8 empty] | 2027-05-16 | 0 | 170 | 2027-05-16 | 0 | 170 | 2027-05-16 | 0 | 170
[8 empty] | 2027-05-17 | 1 | 171 | 2027-05-17 | 1 | 171 | 2027-05-17 | 1 | 171
[8 empty] | 2027-05-18 | 1 | 172 | 2027-05-18 | 1 | 172 | 2027-05-18 | 1 | 172
[8 empty] | 2027-05-19 | 1 | 173 | 2027-05-19 | 1 | 173 | 2027-05-19 | 1 | 173
[8 empty] | 2027-05-20 | 1 | 174 | 2027-05-20 | 1 | 174 | 2027-05-20 | 1 | 174
[8 empty] | 2027-05-21 | 1 | 175 | 2027-05-21 | 1 | 175 | 2027-05-21 | 1 | 175
[8 empty] | 2027-05-22 | 0 | 175 | 2027-05-22 | 0 | 175 | 2027-05-22 | 0 | 175
[8 empty] | 2027-05-23 | 0 | 175 | 2027-05-23 | 0 | 175 | 2027-05-23 | 0 | 175
[8 empty] | 2027-05-24 | 1 | 176 | 2027-05-24 | 1 | 176 | 2027-05-24 | 1 | 176
[8 empty] | 2027-05-25 | 1 | 177 | 2027-05-25 | 1 | 177 | 2027-05-25 | 1 | 177
[8 empty] | 2027-05-26 | 1 | 178 | 2027-05-26 | 1 | 178 | 2027-05-26 | 1 | 178
[8 empty] | 2027-05-27 | 1 | 179 | 2027-05-27 | 1 | 179 | 2027-05-27 | 1 | 179
[8 empty] | 2027-05-28 | 1 | 180 | 2027-05-28 | 1 | 180 | 2027-05-28 | 1 | 180
[8 empty] | 2027-05-29 | 0 | 180 | 2027-05-29 | 0 | 180 | 2027-05-29 | 0 | 180
[8 empty] | 2027-05-30 | 0 | 180 | 2027-05-30 | 0 | 180 | 2027-05-30 | 0 | 180
[8 empty] | 2027-05-31 | 1 | 181 | 2027-05-31 | 1 | 181 | 2027-05-31 | 1 | 181
[8 empty] | 2027-06-01 | 1 | 182 | 2027-06-01 | 1 | 182 | 2027-06-01 | 1 | 182
[8 empty] | 2027-06-02 | 1 | 183 | 2027-06-02 | 1 | 183 | 2027-06-02 | 1 | 183
[8 empty] | 2027-06-03 | 1 | 184 | 2027-06-03 | 1 | 184 | 2027-06-03 | 1 | 184
[8 empty] | 2027-06-04 | 1 | 185 | 2027-06-04 | 1 | 185 | 2027-06-04 | 1 | 185
[8 empty] | 2027-06-05 | 0 | 185 | 2027-06-05 | 0 | 185 | 2027-06-05 | 0 | 185
[8 empty] | 2027-06-06 | 0 | 185 | 2027-06-06 | 0 | 185 | 2027-06-06 | 0 | 185
[8 empty] | 2027-06-07 | 1 | 186 | 2027-06-07 | 1 | 186 | 2027-06-07 | 1 | 186
[8 empty] | 2027-06-08 | 1 | 187 | 2027-06-08 | 1 | 187 | 2027-06-08 | 1 | 187
[8 empty] | 2027-06-09 | 1 | 188 | 2027-06-09 | 1 | 188 | 2027-06-09 | 1 | 188
[8 empty] | 2027-06-10 | 1 | 189 | 2027-06-10 | 1 | 189 | 2027-06-10 | 1 | 189
[8 empty] | 2027-06-11 | 1 | 190 | 2027-06-11 | 1 | 190 | 2027-06-11 | 1 | 190
[8 empty] | 2027-06-12 | 0 | 190 | 2027-06-12 | 0 | 190 | 2027-06-12 | 0 | 190
[8 empty] | 2027-06-13 | 0 | 190 | 2027-06-13 | 0 | 190 | 2027-06-13 | 0 | 190
[8 empty] | 2027-06-14 | 1 | 191 | 2027-06-14 | 1 | 191 | 2027-06-14 | 1 | 191
[8 empty] | 2027-06-15 | 1 | 192 | 2027-06-15 | 1 | 192 | 2027-06-15 | 1 | 192
[8 empty] | 2027-06-16 | 1 | 193 | 2027-06-16 | 1 | 193 | 2027-06-16 | 1 | 193
[8 empty] | 2027-06-17 | 1 | 194 | 2027-06-17 | 1 | 194 | 2027-06-17 | 1 | 194
[8 empty] | 2027-06-18 | 1 | 195 | 2027-06-18 | 1 | 195 | 2027-06-18 | 1 | 195
[8 empty] | 2027-06-19 | 0 | 195 | 2027-06-19 | 0 | 195 | 2027-06-19 | 0 | 195
[8 empty] | 2027-06-20 | 0 | 195 | 2027-06-20 | 0 | 195 | 2027-06-20 | 0 | 195
[8 empty] | 2027-06-21 | 1 | 196 | 2027-06-21 | 1 | 196 | 2027-06-21 | 1 | 196
[8 empty] | 2027-06-22 | 1 | 197 | 2027-06-22 | 1 | 197 | 2027-06-22 | 1 | 197
[8 empty] | 2027-06-23 | 1 | 198 | 2027-06-23 | 1 | 198 | 2027-06-23 | 1 | 198
[8 empty] | 2027-06-24 | 1 | 199 | 2027-06-24 | 1 | 199 | 2027-06-24 | 1 | 199
[8 empty] | 2027-06-25 | 1 | 200 | 2027-06-25 | 1 | 200 | 2027-06-25 | 1 | 200
[8 empty] | 2027-06-26 | 0 | 200 | 2027-06-26 | 0 | 200 | 2027-06-26 | 0 | 200
[8 empty] | 2027-06-27 | 0 | 200 | 2027-06-27 | 0 | 200 | 2027-06-27 | 0 | 200
[8 empty] | 2027-06-28 | 1 | 201 | 2027-06-28 | 1 | 201 | 2027-06-28 | 1 | 201
[8 empty] | 2027-06-29 | 1 | 202 | 2027-06-29 | 1 | 202 | 2027-06-29 | 1 | 202
[8 empty] | 2027-06-30 | 1 | 203 | 2027-06-30 | 1 | 203 | 2027-06-30 | 1 | 203
[8 empty] | 2027-07-01 | 1 | 204 | 2027-07-01 | 1 | 204 | 2027-07-01 | 1 | 204
[8 empty] | 2027-07-02 | 1 | 205 | 2027-07-02 | 1 | 205 | 2027-07-02 | 1 | 205
[8 empty] | 2027-07-03 | 0 | 205 | 2027-07-03 | 0 | 205 | 2027-07-03 | 0 | 205
[8 empty] | 2027-07-04 | 0 | 205 | 2027-07-04 | 0 | 205 | 2027-07-04 | 0 | 205
[8 empty] | 2027-07-05 | 1 | 206 | 2027-07-05 | 1 | 206 | 2027-07-05 | 1 | 206
[8 empty] | 2027-07-06 | 1 | 207 | 2027-07-06 | 1 | 207 | 2027-07-06 | 1 | 207
[8 empty] | 2027-07-07 | 1 | 208 | 2027-07-07 | 1 | 208 | 2027-07-07 | 1 | 208
[8 empty] | 2027-07-08 | 1 | 209 | 2027-07-08 | 1 | 209 | 2027-07-08 | 1 | 209
[8 empty] | 2027-07-09 | 1 | 210 | 2027-07-09 | 1 | 210 | 2027-07-09 | 1 | 210
[8 empty] | 2027-07-10 | 0 | 210 | 2027-07-10 | 0 | 210 | 2027-07-10 | 0 | 210
[8 empty] | 2027-07-11 | 0 | 210 | 2027-07-11 | 0 | 210 | 2027-07-11 | 0 | 210
[8 empty] | 2027-07-12 | 1 | 211 | 2027-07-12 | 1 | 211 | 2027-07-12 | 1 | 211
[8 empty] | 2027-07-13 | 1 | 212 | 2027-07-13 | 1 | 212 | 2027-07-13 | 1 | 212
[8 empty] | 2027-07-14 | 1 | 213 | 2027-07-14 | 1 | 213 | 2027-07-14 | 1 | 213
[8 empty] | 2027-07-15 | 1 | 214 | 2027-07-15 | 1 | 214 | 2027-07-15 | 1 | 214
[8 empty] | 2027-07-16 | 1 | 215 | 2027-07-16 | 1 | 215 | 2027-07-16 | 1 | 215
[8 empty] | 2027-07-17 | 0 | 215 | 2027-07-17 | 0 | 215 | 2027-07-17 | 0 | 215
[8 empty] | 2027-07-18 | 0 | 215 | 2027-07-18 | 0 | 215 | 2027-07-18 | 0 | 215
[8 empty] | 2027-07-19 | 1 | 216 | 2027-07-19 | 1 | 216 | 2027-07-19 | 1 | 216
[8 empty] | 2027-07-20 | 1 | 217 | 2027-07-20 | 1 | 217 | 2027-07-20 | 1 | 217
[8 empty] | 2027-07-21 | 1 | 218 | 2027-07-21 | 1 | 218 | 2027-07-21 | 1 | 218
[8 empty] | 2027-07-22 | 1 | 219 | 2027-07-22 | 1 | 219 | 2027-07-22 | 1 | 219
[8 empty] | 2027-07-23 | 1 | 220 | 2027-07-23 | 1 | 220 | 2027-07-23 | 1 | 220
[8 empty] | 2027-07-24 | 0 | 220 | 2027-07-24 | 0 | 220 | 2027-07-24 | 0 | 220
[8 empty] | 2027-07-25 | 0 | 220 | 2027-07-25 | 0 | 220 | 2027-07-25 | 0 | 220
[8 empty] | 2027-07-26 | 1 | 221 | 2027-07-26 | 1 | 221 | 2027-07-26 | 1 | 221
[8 empty] | 2027-07-27 | 1 | 222 | 2027-07-27 | 1 | 222 | 2027-07-27 | 1 | 222
[8 empty] | 2027-07-28 | 1 | 223 | 2027-07-28 | 1 | 223 | 2027-07-28 | 1 | 223
[8 empty] | 2027-07-29 | 1 | 224 | 2027-07-29 | 1 | 224 | 2027-07-29 | 1 | 224
[8 empty] | 2027-07-30 | 1 | 225 | 2027-07-30 | 1 | 225 | 2027-07-30 | 1 | 225
[8 empty] | 2027-07-31 | 0 | 225 | 2027-07-31 | 0 | 225 | 2027-07-31 | 0 | 225
[8 empty] | 2027-08-01 | 0 | 225 | 2027-08-01 | 0 | 225 | 2027-08-01 | 0 | 225
[8 empty] | 2027-08-02 | 1 | 226 | 2027-08-02 | 1 | 226 | 2027-08-02 | 1 | 226
[8 empty] | 2027-08-03 | 1 | 227 | 2027-08-03 | 1 | 227 | 2027-08-03 | 1 | 227
[8 empty] | 2027-08-04 | 1 | 228 | 2027-08-04 | 1 | 228 | 2027-08-04 | 1 | 228
[8 empty] | 2027-08-05 | 1 | 229 | 2027-08-05 | 1 | 229 | 2027-08-05 | 1 | 229
[8 empty] | 2027-08-06 | 1 | 230 | 2027-08-06 | 1 | 230 | 2027-08-06 | 1 | 230
[8 empty] | 2027-08-07 | 0 | 230 | 2027-08-07 | 0 | 230 | 2027-08-07 | 0 | 230
[8 empty] | 2027-08-08 | 0 | 230 | 2027-08-08 | 0 | 230 | 2027-08-08 | 0 | 230
[8 empty] | 2027-08-09 | 1 | 231 | 2027-08-09 | 1 | 231 | 2027-08-09 | 1 | 231
[8 empty] | 2027-08-10 | 1 | 232 | 2027-08-10 | 1 | 232 | 2027-08-10 | 1 | 232
[8 empty] | 2027-08-11 | 1 | 233 | 2027-08-11 | 1 | 233 | 2027-08-11 | 1 | 233
[8 empty] | 2027-08-12 | 1 | 234 | 2027-08-12 | 1 | 234 | 2027-08-12 | 1 | 234
[8 empty] | 2027-08-13 | 1 | 235 | 2027-08-13 | 1 | 235 | 2027-08-13 | 1 | 235
[8 empty] | 2027-08-14 | 0 | 235 | 2027-08-14 | 0 | 235 | 2027-08-14 | 0 | 235
[8 empty] | 2027-08-15 | 0 | 235 | 2027-08-15 | 0 | 235 | 2027-08-15 | 0 | 235
[8 empty] | 2027-08-16 | 1 | 236 | 2027-08-16 | 1 | 236 | 2027-08-16 | 1 | 236
[8 empty] | 2027-08-17 | 1 | 237 | 2027-08-17 | 1 | 237 | 2027-08-17 | 1 | 237
[8 empty] | 2027-08-18 | 1 | 238 | 2027-08-18 | 1 | 238 | 2027-08-18 | 1 | 238
[8 empty] | 2027-08-19 | 1 | 239 | 2027-08-19 | 1 | 239 | 2027-08-19 | 1 | 239
[8 empty] | 2027-08-20 | 1 | 240 | 2027-08-20 | 1 | 240 | 2027-08-20 | 1 | 240
[8 empty] | 2027-08-21 | 0 | 240 | 2027-08-21 | 0 | 240 | 2027-08-21 | 0 | 240
[8 empty] | 2027-08-22 | 0 | 240 | 2027-08-22 | 0 | 240 | 2027-08-22 | 0 | 240
[8 empty] | 2027-08-23 | 1 | 241 | 2027-08-23 | 1 | 241 | 2027-08-23 | 1 | 241
[8 empty] | 2027-08-24 | 1 | 242 | 2027-08-24 | 1 | 242 | 2027-08-24 | 1 | 242
[8 empty] | 2027-08-25 | 1 | 243 | 2027-08-25 | 1 | 243 | 2027-08-25 | 1 | 243
[8 empty] | 2027-08-26 | 1 | 244 | 2027-08-26 | 1 | 244 | 2027-08-26 | 1 | 244
[8 empty] | 2027-08-27 | 1 | 245 | 2027-08-27 | 1 | 245 | 2027-08-27 | 1 | 245
[8 empty] | 2027-08-28 | 0 | 245 | 2027-08-28 | 0 | 245 | 2027-08-28 | 0 | 245
[8 empty] | 2027-08-29 | 0 | 245 | 2027-08-29 | 0 | 245 | 2027-08-29 | 0 | 245
[8 empty] | 2027-08-30 | 1 | 246 | 2027-08-30 | 1 | 246 | 2027-08-30 | 1 | 246
[8 empty] | 2027-08-31 | 1 | 247 | 2027-08-31 | 1 | 247 | 2027-08-31 | 1 | 247
[8 empty] | 2027-09-01 | 1 | 248 | 2027-09-01 | 1 | 248 | 2027-09-01 | 1 | 248
[8 empty] | 2027-09-02 | 1 | 249 | 2027-09-02 | 1 | 249 | 2027-09-02 | 1 | 249
[8 empty] | 2027-09-03 | 1 | 250 | 2027-09-03 | 1 | 250 | 2027-09-03 | 1 | 250
[8 empty] | 2027-09-04 | 0 | 250 | 2027-09-04 | 0 | 250 | 2027-09-04 | 0 | 250
[8 empty] | 2027-09-05 | 0 | 250 | 2027-09-05 | 0 | 250 | 2027-09-05 | 0 | 250
[8 empty] | 2027-09-06 | 1 | 251 | 2027-09-06 | 1 | 251 | 2027-09-06 | 1 | 251
[8 empty] | 2027-09-07 | 1 | 252 | 2027-09-07 | 1 | 252 | 2027-09-07 | 1 | 252
[8 empty] | 2027-09-08 | 1 | 253 | 2027-09-08 | 1 | 253 | 2027-09-08 | 1 | 253
[8 empty] | 2027-09-09 | 1 | 254 | 2027-09-09 | 1 | 254 | 2027-09-09 | 1 | 254
[8 empty] | 2027-09-10 | 1 | 255 | 2027-09-10 | 1 | 255 | 2027-09-10 | 1 | 255
[8 empty] | 2027-09-11 | 0 | 255 | 2027-09-11 | 0 | 255 | 2027-09-11 | 0 | 255
[8 empty] | 2027-09-12 | 0 | 255 | 2027-09-12 | 0 | 255 | 2027-09-12 | 0 | 255
[8 empty] | 2027-09-13 | 1 | 256 | 2027-09-13 | 1 | 256 | 2027-09-13 | 1 | 256
[8 empty] | 2027-09-14 | 1 | 257 | 2027-09-14 | 1 | 257 | 2027-09-14 | 1 | 257
[8 empty] | 2027-09-15 | 1 | 258 | 2027-09-15 | 1 | 258 | 2027-09-15 | 1 | 258
[8 empty] | 2027-09-16 | 1 | 259 | 2027-09-16 | 1 | 259 | 2027-09-16 | 1 | 259
[8 empty] | 2027-09-17 | 1 | 260 | 2027-09-17 | 1 | 260 | 2027-09-17 | 1 | 260
[8 empty] | 2027-09-18 | 0 | 260 | 2027-09-18 | 0 | 260 | 2027-09-18 | 0 | 260
[8 empty] | 2027-09-19 | 0 | 260 | 2027-09-19 | 0 | 260 | 2027-09-19 | 0 | 260
[8 empty] | 2027-09-20 | 1 | 261 | 2027-09-20 | 1 | 261 | 2027-09-20 | 1 | 261
[8 empty] | 2027-09-21 | 1 | 262 | 2027-09-21 | 1 | 262 | 2027-09-21 | 1 | 262
[8 empty] | 2027-09-22 | 1 | 263 | 2027-09-22 | 1 | 263 | 2027-09-22 | 1 | 263
[8 empty] | 2027-09-23 | 1 | 264 | 2027-09-23 | 1 | 264 | 2027-09-23 | 1 | 264
[8 empty] | 2027-09-24 | 1 | 265 | 2027-09-24 | 1 | 265 | 2027-09-24 | 1 | 265
[8 empty] | 2027-09-25 | 0 | 265 | 2027-09-25 | 0 | 265 | 2027-09-25 | 0 | 265
[8 empty] | 2027-09-26 | 0 | 265 | 2027-09-26 | 0 | 265 | 2027-09-26 | 0 | 265
[8 empty] | 2027-09-27 | 1 | 266 | 2027-09-27 | 1 | 266 | 2027-09-27 | 1 | 266
[8 empty] | 2027-09-28 | 1 | 267 | 2027-09-28 | 1 | 267 | 2027-09-28 | 1 | 267
[8 empty] | 2027-09-29 | 1 | 268 | 2027-09-29 | 1 | 268 | 2027-09-29 | 1 | 268
[8 empty] | 2027-09-30 | 1 | 269 | 2027-09-30 | 1 | 269 | 2027-09-30 | 1 | 269
[8 empty] | 2027-10-01 | 1 | 270 | 2027-10-01 | 1 | 270 | 2027-10-01 | 1 | 270
[8 empty] | 2027-10-02 | 0 | 270 | 2027-10-02 | 0 | 270 | 2027-10-02 | 0 | 270
[8 empty] | 2027-10-03 | 0 | 270 | 2027-10-03 | 0 | 270 | 2027-10-03 | 0 | 270
[8 empty] | 2027-10-04 | 1 | 271 | 2027-10-04 | 1 | 271 | 2027-10-04 | 1 | 271
[8 empty] | 2027-10-05 | 1 | 272 | 2027-10-05 | 1 | 272 | 2027-10-05 | 1 | 272
[8 empty] | 2027-10-06 | 1 | 273 | 2027-10-06 | 1 | 273 | 2027-10-06 | 1 | 273
[8 empty] | 2027-10-07 | 1 | 274 | 2027-10-07 | 1 | 274 | 2027-10-07 | 1 | 274
[8 empty] | 2027-10-08 | 1 | 275 | 2027-10-08 | 1 | 275 | 2027-10-08 | 1 | 275
[8 empty] | 2027-10-09 | 0 | 275 | 2027-10-09 | 0 | 275 | 2027-10-09 | 0 | 275
[8 empty] | 2027-10-10 | 0 | 275 | 2027-10-10 | 0 | 275 | 2027-10-10 | 0 | 275
[8 empty] | 2027-10-11 | 1 | 276 | 2027-10-11 | 1 | 276 | 2027-10-11 | 1 | 276
[8 empty] | 2027-10-12 | 1 | 277 | 2027-10-12 | 1 | 277 | 2027-10-12 | 1 | 277
[8 empty] | 2027-10-13 | 1 | 278 | 2027-10-13 | 1 | 278 | 2027-10-13 | 1 | 278
[8 empty] | 2027-10-14 | 1 | 279 | 2027-10-14 | 1 | 279 | 2027-10-14 | 1 | 279
[8 empty] | 2027-10-15 | 1 | 280 | 2027-10-15 | 1 | 280 | 2027-10-15 | 1 | 280
[8 empty] | 2027-10-16 | 0 | 280 | 2027-10-16 | 0 | 280 | 2027-10-16 | 0 | 280
[8 empty] | 2027-10-17 | 0 | 280 | 2027-10-17 | 0 | 280 | 2027-10-17 | 0 | 280
[8 empty] | 2027-10-18 | 1 | 281 | 2027-10-18 | 1 | 281 | 2027-10-18 | 1 | 281
[8 empty] | 2027-10-19 | 1 | 282 | 2027-10-19 | 1 | 282 | 2027-10-19 | 1 | 282
[8 empty] | 2027-10-20 | 1 | 283 | 2027-10-20 | 1 | 283 | 2027-10-20 | 1 | 283
[8 empty] | 2027-10-21 | 1 | 284 | 2027-10-21 | 1 | 284 | 2027-10-21 | 1 | 284
[8 empty] | 2027-10-22 | 1 | 285 | 2027-10-22 | 1 | 285 | 2027-10-22 | 1 | 285
[8 empty] | 2027-10-23 | 0 | 285 | 2027-10-23 | 0 | 285 | 2027-10-23 | 0 | 285
[8 empty] | 2027-10-24 | 0 | 285 | 2027-10-24 | 0 | 285 | 2027-10-24 | 0 | 285
[8 empty] | 2027-10-25 | 1 | 286 | 2027-10-25 | 1 | 286 | 2027-10-25 | 1 | 286
[8 empty] | 2027-10-26 | 1 | 287 | 2027-10-26 | 1 | 287 | 2027-10-26 | 1 | 287
[8 empty] | 2027-10-27 | 1 | 288 | 2027-10-27 | 1 | 288 | 2027-10-27 | 1 | 288
[8 empty] | 2027-10-28 | 1 | 289 | 2027-10-28 | 1 | 289 | 2027-10-28 | 1 | 289
[8 empty] | 2027-10-29 | 1 | 290 | 2027-10-29 | 1 | 290 | 2027-10-29 | 1 | 290
[8 empty] | 2027-10-30 | 0 | 290 | 2027-10-30 | 0 | 290 | 2027-10-30 | 0 | 290
[8 empty] | 2027-10-31 | 0 | 290 | 2027-10-31 | 0 | 290 | 2027-10-31 | 0 | 290
[8 empty] | 2027-11-01 | 1 | 291 | 2027-11-01 | 1 | 291 | 2027-11-01 | 1 | 291
[8 empty] | 2027-11-02 | 1 | 292 | 2027-11-02 | 1 | 292 | 2027-11-02 | 1 | 292
[8 empty] | 2027-11-03 | 1 | 293 | 2027-11-03 | 1 | 293 | 2027-11-03 | 1 | 293
[8 empty] | 2027-11-04 | 1 | 294 | 2027-11-04 | 1 | 294 | 2027-11-04 | 1 | 294
[8 empty] | 2027-11-05 | 1 | 295 | 2027-11-05 | 1 | 295 | 2027-11-05 | 1 | 295
[8 empty] | 2027-11-06 | 0 | 295 | 2027-11-06 | 0 | 295 | 2027-11-06 | 0 | 295
[8 empty] | 2027-11-07 | 0 | 295 | 2027-11-07 | 0 | 295 | 2027-11-07 | 0 | 295
[8 empty] | 2027-11-08 | 1 | 296 | 2027-11-08 | 1 | 296 | 2027-11-08 | 1 | 296
[8 empty] | 2027-11-09 | 1 | 297 | 2027-11-09 | 1 | 297 | 2027-11-09 | 1 | 297
[8 empty] | 2027-11-10 | 1 | 298 | 2027-11-10 | 1 | 298 | 2027-11-10 | 1 | 298
[8 empty] | 2027-11-11 | 1 | 299 | 2027-11-11 | 1 | 299 | 2027-11-11 | 1 | 299
[8 empty] | 2027-11-12 | 1 | 300 | 2027-11-12 | 1 | 300 | 2027-11-12 | 1 | 300
[8 empty] | 2027-11-13 | 0 | 300 | 2027-11-13 | 0 | 300 | 2027-11-13 | 0 | 300
[8 empty] | 2027-11-14 | 0 | 300 | 2027-11-14 | 0 | 300 | 2027-11-14 | 0 | 300
[8 empty] | 2027-11-15 | 1 | 301 | 2027-11-15 | 1 | 301 | 2027-11-15 | 1 | 301
[8 empty] | 2027-11-16 | 1 | 302 | 2027-11-16 | 1 | 302 | 2027-11-16 | 1 | 302
[8 empty] | 2027-11-17 | 1 | 303 | 2027-11-17 | 1 | 303 | 2027-11-17 | 1 | 303
[8 empty] | 2027-11-18 | 1 | 304 | 2027-11-18 | 1 | 304 | 2027-11-18 | 1 | 304
[8 empty] | 2027-11-19 | 1 | 305 | 2027-11-19 | 1 | 305 | 2027-11-19 | 1 | 305
[8 empty] | 2027-11-20 | 0 | 305 | 2027-11-20 | 0 | 305 | 2027-11-20 | 0 | 305
[8 empty] | 2027-11-21 | 0 | 305 | 2027-11-21 | 0 | 305 | 2027-11-21 | 0 | 305
[8 empty] | 2027-11-22 | 1 | 306 | 2027-11-22 | 1 | 306 | 2027-11-22 | 1 | 306
[8 empty] | 2027-11-23 | 1 | 307 | 2027-11-23 | 1 | 307 | 2027-11-23 | 1 | 307
[8 empty] | 2027-11-24 | 1 | 308 | 2027-11-24 | 1 | 308 | 2027-11-24 | 1 | 308
[8 empty] | 2027-11-25 | 1 | 309 | 2027-11-25 | 1 | 309 | 2027-11-25 | 1 | 309
[8 empty] | 2027-11-26 | 1 | 310 | 2027-11-26 | 1 | 310 | 2027-11-26 | 1 | 310
[8 empty] | 2027-11-27 | 0 | 310 | 2027-11-27 | 0 | 310 | 2027-11-27 | 0 | 310
[8 empty] | 2027-11-28 | 0 | 310 | 2027-11-28 | 0 | 310 | 2027-11-28 | 0 | 310
[8 empty] | 2027-11-29 | 1 | 311 | 2027-11-29 | 1 | 311 | 2027-11-29 | 1 | 311
[8 empty] | 2027-11-30 | 1 | 312 | 2027-11-30 | 1 | 312 | 2027-11-30 | 1 | 312
[8 empty] | 2027-12-01 | 1 | 313 | 2027-12-01 | 1 | 313 | 2027-12-01 | 1 | 313
[8 empty] | 2027-12-02 | 1 | 314 | 2027-12-02 | 1 | 314 | 2027-12-02 | 1 | 314
[8 empty] | 2027-12-03 | 1 | 315 | 2027-12-03 | 1 | 315 | 2027-12-03 | 1 | 315
[8 empty] | 2027-12-04 | 0 | 315 | 2027-12-04 | 0 | 315 | 2027-12-04 | 0 | 315
[8 empty] | 2027-12-05 | 0 | 315 | 2027-12-05 | 0 | 315 | 2027-12-05 | 0 | 315
[8 empty] | 2027-12-06 | 1 | 316 | 2027-12-06 | 1 | 316 | 2027-12-06 | 1 | 316
[8 empty] | 2027-12-07 | 1 | 317 | 2027-12-07 | 1 | 317 | 2027-12-07 | 1 | 317
[8 empty] | 2027-12-08 | 1 | 318 | 2027-12-08 | 1 | 318 | 2027-12-08 | 1 | 318
[8 empty] | 2027-12-09 | 1 | 319 | 2027-12-09 | 1 | 319 | 2027-12-09 | 1 | 319
[8 empty] | 2027-12-10 | 1 | 320 | 2027-12-10 | 1 | 320 | 2027-12-10 | 1 | 320
[8 empty] | 2027-12-11 | 0 | 320 | 2027-12-11 | 0 | 320 | 2027-12-11 | 0 | 320
[8 empty] | 2027-12-12 | 0 | 320 | 2027-12-12 | 0 | 320 | 2027-12-12 | 0 | 320
[8 empty] | 2027-12-13 | 1 | 321 | 2027-12-13 | 1 | 321 | 2027-12-13 | 1 | 321
[8 empty] | 2027-12-14 | 1 | 322 | 2027-12-14 | 1 | 322 | 2027-12-14 | 1 | 322
[8 empty] | 2027-12-15 | 1 | 323 | 2027-12-15 | 1 | 323 | 2027-12-15 | 1 | 323
[8 empty] | 2027-12-16 | 1 | 324 | 2027-12-16 | 1 | 324 | 2027-12-16 | 1 | 324
[8 empty] | 2027-12-17 | 1 | 325 | 2027-12-17 | 1 | 325 | 2027-12-17 | 1 | 325
[8 empty] | 2027-12-18 | 0 | 325 | 2027-12-18 | 0 | 325 | 2027-12-18 | 0 | 325
[8 empty] | 2027-12-19 | 0 | 325 | 2027-12-19 | 0 | 325 | 2027-12-19 | 0 | 325
[8 empty] | 2027-12-20 | 1 | 326 | 2027-12-20 | 1 | 326 | 2027-12-20 | 1 | 326
[8 empty] | 2027-12-21 | 1 | 327 | 2027-12-21 | 1 | 327 | 2027-12-21 | 1 | 327
[8 empty] | 2027-12-22 | 1 | 328 | 2027-12-22 | 1 | 328 | 2027-12-22 | 1 | 328
[8 empty] | 2027-12-23 | 1 | 329 | 2027-12-23 | 1 | 329 | 2027-12-23 | 1 | 329
[8 empty] | 2027-12-24 | 1 | 330 | 2027-12-24 | 1 | 330 | 2027-12-24 | 1 | 330
[8 empty] | 2027-12-25 | 0 | 330 | 2027-12-25 | 0 | 330 | 2027-12-25 | 0 | 330
[8 empty] | 2027-12-26 | 0 | 330 | 2027-12-26 | 0 | 330 | 2027-12-26 | 0 | 330
[8 empty] | 2027-12-27 | 1 | 331 | 2027-12-27 | 1 | 331 | 2027-12-27 | 1 | 331
[8 empty] | 2027-12-28 | 1 | 332 | 2027-12-28 | 1 | 332 | 2027-12-28 | 1 | 332
[8 empty] | 2027-12-29 | 1 | 333 | 2027-12-29 | 1 | 333 | 2027-12-29 | 1 | 333
[8 empty] | 2027-12-30 | 1 | 334 | 2027-12-30 | 1 | 334 | 2027-12-30 | 1 | 334
[8 empty] | 2027-12-31 | 1 | 335 | 2027-12-31 | 1 | 335 | 2027-12-31 | 1 | 335
[8 empty] | 2028-01-01 | 0 | 335 | 2028-01-01 | 0 | 335 | 2028-01-01 | 0 | 335
[8 empty] | 2028-01-02 | 0 | 335 | 2028-01-02 | 0 | 335 | 2028-01-02 | 0 | 335
[8 empty] | 2028-01-03 | 1 | 336 | 2028-01-03 | 1 | 336 | 2028-01-03 | 1 | 336
[8 empty] | 2028-01-04 | 1 | 337 | 2028-01-04 | 1 | 337 | 2028-01-04 | 1 | 337
[8 empty] | 2028-01-05 | 1 | 338 | 2028-01-05 | 1 | 338 | 2028-01-05 | 1 | 338
[8 empty] | 2028-01-06 | 1 | 339 | 2028-01-06 | 1 | 339 | 2028-01-06 | 1 | 339
[8 empty] | 2028-01-07 | 1 | 340 | 2028-01-07 | 1 | 340 | 2028-01-07 | 1 | 340
[8 empty] | 2028-01-08 | 0 | 340 | 2028-01-08 | 0 | 340 | 2028-01-08 | 0 | 340
[8 empty] | 2028-01-09 | 0 | 340 | 2028-01-09 | 0 | 340 | 2028-01-09 | 0 | 340
[8 empty] | 2028-01-10 | 1 | 341 | 2028-01-10 | 1 | 341 | 2028-01-10 | 1 | 341
[8 empty] | 2028-01-11 | 1 | 342 | 2028-01-11 | 1 | 342 | 2028-01-11 | 1 | 342
[8 empty] | 2028-01-12 | 1 | 343 | 2028-01-12 | 1 | 343 | 2028-01-12 | 1 | 343
[8 empty] | 2028-01-13 | 1 | 344 | 2028-01-13 | 1 | 344 | 2028-01-13 | 1 | 344
[8 empty] | 2028-01-14 | 1 | 345 | 2028-01-14 | 1 | 345 | 2028-01-14 | 1 | 345
[8 empty] | 2028-01-15 | 0 | 345 | 2028-01-15 | 0 | 345 | 2028-01-15 | 0 | 345
[8 empty] | 2028-01-16 | 0 | 345 | 2028-01-16 | 0 | 345 | 2028-01-16 | 0 | 345
[8 empty] | 2028-01-17 | 1 | 346 | 2028-01-17 | 1 | 346 | 2028-01-17 | 1 | 346
[8 empty] | 2028-01-18 | 1 | 347 | 2028-01-18 | 1 | 347 | 2028-01-18 | 1 | 347
[8 empty] | 2028-01-19 | 1 | 348 | 2028-01-19 | 1 | 348 | 2028-01-19 | 1 | 348
[8 empty] | 2028-01-20 | 1 | 349 | 2028-01-20 | 1 | 349 | 2028-01-20 | 1 | 349
[8 empty] | 2028-01-21 | 1 | 350 | 2028-01-21 | 1 | 350 | 2028-01-21 | 1 | 350
[8 empty] | 2028-01-22 | 0 | 350 | 2028-01-22 | 0 | 350 | 2028-01-22 | 0 | 350
[8 empty] | 2028-01-23 | 0 | 350 | 2028-01-23 | 0 | 350 | 2028-01-23 | 0 | 350
[8 empty] | 2028-01-24 | 1 | 351 | 2028-01-24 | 1 | 351 | 2028-01-24 | 1 | 351
[8 empty] | 2028-01-25 | 1 | 352 | 2028-01-25 | 1 | 352 | 2028-01-25 | 1 | 352
[8 empty] | 2028-01-26 | 1 | 353 | 2028-01-26 | 1 | 353 | 2028-01-26 | 1 | 353
[8 empty] | 2028-01-27 | 1 | 354 | 2028-01-27 | 1 | 354 | 2028-01-27 | 1 | 354
[8 empty] | 2028-01-28 | 1 | 355 | 2028-01-28 | 1 | 355 | 2028-01-28 | 1 | 355
[8 empty] | 2028-01-29 | 0 | 355 | 2028-01-29 | 0 | 355 | 2028-01-29 | 0 | 355
[8 empty] | 2028-01-30 | 0 | 355 | 2028-01-30 | 0 | 355 | 2028-01-30 | 0 | 355
[8 empty] | 2028-01-31 | 1 | 356 | 2028-01-31 | 1 | 356 | 2028-01-31 | 1 | 356
[8 empty] | 2028-02-01 | 1 | 357 | 2028-02-01 | 1 | 357 | 2028-02-01 | 1 | 357
[8 empty] | 2028-02-02 | 1 | 358 | 2028-02-02 | 1 | 358 | 2028-02-02 | 1 | 358
Formulas:
Date = [Date, row above]+1

## Tier 1 Consumers
Tier 1: Report Consumers: 4 sessions x 2 hours
Audience: Managers, executives and business users who read and act on dashboards. Yellow columns are yours to edit; dates come from the Schedule Planner sheet.
Session | Training Day # | Date | Day | Module | Topic | Key Concepts | Hands-on Lab | Planned Hrs | Status | Actual Hrs | Notes / Mistakes Log
1 | 1 | 2026-09-21 | 2026-09-21 | 1. Power BI Foundations | Power BI orientation & navigation | What Power BI is; Desktop vs Service vs Mobile (what consumers actually use); workspaces, apps, reports vs dashboards; Home, Browse, Favourites, Recent; checking data freshness (last refresh) | Sign in, find and favourite three reports, open an app, locate the last refresh time | 2 | Not Started
2 | 2 | 2026-09-22 | 2026-09-22 | 2. Explore & Interact with Reports | Reading visuals correctly | Best-fit visual by data relationship: clustered bar/column (comparison), line (trend over time), stacked bar or treemap (part-to-whole), scatter (correlation), waterfall (variance/bridge), sorted bar (ranking), card/KPI (single value), table/matrix (detail), filled or bubble map (geography); reading axes, legends and totals; common misreads (truncated axes, dual axes, overloaded pies) | Interpret a supplied sales dashboard and answer 10 business questions | 2 | Not Started
3 | 3 | 2026-09-23 | 2026-09-23 | 2. Explore & Interact with Reports | Interacting with reports | Slicers and the filters pane; cross-filtering and highlighting; drill-down and drillthrough; bookmarks and tooltips; Personalise visuals; See data / Show as table; Q&A and Copilot (if licensed) | Answer business questions from a live report using interaction only | 2 | Not Started
4 | 4 | 2026-09-24 | 2026-09-24 | 3. Share & Stay Informed | Sharing, alerts & data handling | Export to Excel / PDF / PowerPoint and its limits; Analyze in Excel; subscriptions and alerts; mobile app; sharing and permission awareness; sensitivity labels and responsible data use; raising a data issue; end-of-course knowledge check | Set up a subscription and an alert, export a filtered view, complete the knowledge check | 2 | Not Started
Total | [7 empty] | 8 | 0 / 4 | 0
Formulas:
Date = IFERROR(INDEX('Schedule Planner'!$K5:K504,MATCH([Training Day #],'Schedule Planner'!$M5:M504,0)),"Set training days")
Day = IF(ISNUMBER([Date]),[Date],"")

## Tier 2 Creators
Tier 2: Report Creators: 12 sessions x 2 hours
Audience: Business, finance and MIS analysts who build reports from existing or simple datasets. Yellow columns are yours to edit; dates come from the Schedule Planner sheet.
Session | Training Day # | Date | Day | Module | Topic | Key Concepts | Hands-on Lab | Planned Hrs | Status | Actual Hrs | Notes / Mistakes Log
1 | 1 | 2026-09-21 | 2026-09-21 | 1. Data Connect & Data Preparation | Power BI overview & connecting to data | Desktop-to-Service workflow; Import vs DirectQuery (when each is used); connecting to Excel, CSV, SQL Server and SharePoint; credentials and privacy levels | Install Desktop, connect to three sources and load them | 2 | Not Started
2 | 2 | 2026-09-22 | 2026-09-22 | 1. Data Connect & Data Preparation | Cleaning data with Power Query | Power Query Editor and applied steps; column profiling; data types; errors and blanks; trim, replace, split, fill down, remove duplicates; filtering rows | Clean a messy sales extract | 2 | Not Started
3 | 3 | 2026-09-23 | 2026-09-23 | 1. Data Connect & Data Preparation | Shaping & combining data | Merge and append queries; Group By; pivot and unpivot; conditional and custom columns; combining files from a folder | Combine sales, customer and product tables; Module 1 checkpoint quiz | 2 | Not Started
4 | 4 | 2026-09-24 | 2026-09-24 | 2. Data Model & DAX (Core) | Star schema & relationships | Fact vs dimension tables; cardinality; cross-filter direction; active vs inactive relationships; building and marking a date table | Build a star schema and test the relationships with a matrix | 2 | Not Started
5 | 5 | 2026-09-25 | 2026-09-25 | 2. Data Model & DAX (Core) | Model tidy-up & DAX fundamentals | Hide fields, formats, hierarchies, sort by column; calculated columns vs measures; SUM, AVERAGE, COUNT, DISTINCTCOUNT, DIVIDE | Write 8 core measures and organise them in a measures table | 2 | Not Started
6 | 6 | 2026-09-28 | 2026-09-28 | 2. Data Model & DAX (Core) | CALCULATE & filter context | Row vs filter context (intro); CALCULATE; FILTER; ALL and REMOVEFILTERS; percent of total; variables (VAR / RETURN) | Percent of total, filtered totals and a ranking measure | 2 | Not Started
7 | 7 | 2026-09-29 | 2026-09-29 | 2. Data Model & DAX (Core) | Time intelligence basics | Date table requirements; TOTALYTD, SAMEPERIODLASTYEAR, DATEADD; month-on-month and year-on-year change | Build YoY, MTD and YTD measures; Module 2 checkpoint quiz | 2 | Not Started
8 | 8 | 2026-09-30 | 2026-09-30 | 3. Visualisations | Choosing the right visual | Best-fit visual by data relationship: clustered bar/column (comparison), line (trend over time), stacked bar or treemap (part-to-whole), scatter (correlation), waterfall (variance/bridge), sorted bar (ranking), card/KPI (single value), table/matrix (detail), filled or bubble map (geography) | Build one visual for each relationship type | 2 | Not Started
9 | 9 | 2026-10-01 | 2026-10-01 | 3. Visualisations | Report design & accessibility | Page layout, themes and alignment; titles and labels; colour contrast; alt text and tab order; mobile layout | Design a three-page report using a custom theme | 2 | Not Started
10 | 10 | 2026-10-02 | 2026-10-02 | 3. Visualisations | Interactivity & navigation | Slicers and synced slicers; filters pane; edit interactions; drill-down and drillthrough; bookmarks and buttons; tooltip pages | Build a navigation menu with a drillthrough page | 2 | Not Started
11 | 11 | 2026-10-05 | 2026-10-05 | 3. Visualisations | Analytics, conditional formatting & AI visuals | Conditional formatting; reference lines; Top N; forecasting; key influencers; decomposition tree; smart narrative | Highlight outliers and explain a KPI change with an AI visual; Module 3 checkpoint quiz | 2 | Not Started
12 | 12 | 2026-10-06 | 2026-10-06 | 4. Maintenance & Security (Essentials) | Publish, share & capstone | Publishing to the Service; workspaces and roles; apps; scheduled refresh basics; awareness of row-level security and sensitivity labels | Publish a capstone report built on company data and present it for review (rubric scored) | 2 | Not Started
Total | [7 empty] | 24 | 0 / 12 | 0
Formulas:
Date = IFERROR(INDEX('Schedule Planner'!$N5:N504,MATCH([Training Day #],'Schedule Planner'!$P5:P504,0)),"Set training days")
Day = IF(ISNUMBER([Date]),[Date],"")

## Tier 3 Builders
Tier 3: Data & Model Builders: 30 sessions x 2 hours
Audience: BI developers and reporting analysts who own and maintain datasets (PL-300 equivalent). Yellow columns are yours to edit; dates come from the Schedule Planner sheet.
Session | Training Day # | Date | Day | Module | Topic | Key Concepts | Hands-on Lab | Planned Hrs | Status | Actual Hrs | Notes / Mistakes Log
1 | 1 | 2026-09-21 | 2026-09-21 | 1. Data Connect & Data Preparation | Power BI ecosystem & connectivity modes | Desktop, Service and Mobile; report lifecycle; Import vs DirectQuery vs Dual vs Live Connection and when to use each | Install Desktop, tour the interface, connect to a first Excel file | 2 | Not Started
2 | 2 | 2026-09-22 | 2026-09-22 | 1. Data Connect & Data Preparation | Connecting to data sources | Excel, CSV, SQL Server, SharePoint, web and folder sources; credentials, privacy levels, data source settings | Load data from three different source types | 2 | Not Started
3 | 3 | 2026-09-23 | 2026-09-23 | 1. Data Connect & Data Preparation | Power Query basics & data profiling | Power Query Editor, applied steps, column quality / distribution / profile, data types, errors and empty values | Clean a messy file: trim, replace, split, fill down, remove duplicates | 2 | Not Started
4 | 4 | 2026-09-24 | 2026-09-24 | 1. Data Connect & Data Preparation | Shaping & combining data | Pivot, unpivot, transpose; merge queries (all join types); append; Group By; conditional and custom columns | Combine sales, customer and product tables | 2 | Not Started
5 | 5 | 2026-09-25 | 2026-09-25 | 1. Data Connect & Data Preparation | Advanced Power Query | M language basics, parameters, custom functions; reference vs duplicate queries; combine files from a folder; query folding; staging queries | Build a folder-based monthly file ingestion | 2 | Not Started
6 | 6 | 2026-09-28 | 2026-09-28 | 1. Data Connect & Data Preparation | Preparing data for the model | Shaping fact and dimension tables; building a date table; fixing import errors and load performance; dataflows and incremental refresh concepts | Create a clean star-schema-ready dataset | 2 | Not Started
7 | 7 | 2026-09-29 | 2026-09-29 | 1. Data Connect & Data Preparation | Module 1 checkpoint | Review of the whole domain; 20-question quiz; fix gaps | End-to-end: raw files to a fully prepared dataset | 2 | Not Started
8 | 8 | 2026-09-30 | 2026-09-30 | 2. Data Model & DAX | Star schema & model design | Fact vs dimension tables, granularity, normalisation vs denormalisation, Model view and table properties | Build a star schema from the Module 1 data | 2 | Not Started
9 | 9 | 2026-10-01 | 2026-10-01 | 2. Data Model & DAX | Relationships | Cardinality, cross-filter direction, active vs inactive relationships, many-to-many, role-playing dimensions | Create and troubleshoot relationships, including a role-playing date table | 2 | Not Started
10 | 10 | 2026-10-02 | 2026-10-02 | 2. Data Model & DAX | Model properties & usability | Hide fields, sort by column, data categories, formatting, hierarchies, display folders | Tidy the model as if handing it to a business user | 2 | Not Started
11 | 11 | 2026-10-05 | 2026-10-05 | 2. Data Model & DAX | DAX fundamentals | Calculated columns vs measures vs tables; implicit vs explicit measures; row context vs filter context | Write 10 basic measures (SUM, AVERAGE, COUNT, DIVIDE) | 2 | Not Started
12 | 12 | 2026-10-06 | 2026-10-06 | 2. Data Model & DAX | CALCULATE & filter functions | CALCULATE, FILTER, ALL, ALLEXCEPT, REMOVEFILTERS, VALUES, KEEPFILTERS | Percent of total, filtered totals, year-to-date comparisons | 2 | Not Started
13 | 13 | 2026-10-07 | 2026-10-07 | 2. Data Model & DAX | Iterators, logic & text functions | SUMX, AVERAGEX, RANKX, COUNTROWS, DISTINCTCOUNT; IF, SWITCH; text functions | Ranking, running totals and category buckets | 2 | Not Started
14 | 14 | 2026-10-08 | 2026-10-08 | 2. Data Model & DAX | Time intelligence | Marking a date table; TOTALYTD, SAMEPERIODLASTYEAR, DATEADD, DATESINPERIOD; rolling averages | Full set of YoY, MTD, QTD and rolling 3-month measures | 2 | Not Started
15 | 15 | 2026-10-09 | 2026-10-09 | 2. Data Model & DAX | Advanced modelling features | Variables (VAR/RETURN), USERELATIONSHIP, field parameters, what-if parameters, calculation groups, composite models, aggregations | Add a what-if scenario and a dynamic measure selector | 2 | Not Started
16 | 16 | 2026-10-12 | 2026-10-12 | 2. Data Model & DAX | Performance optimisation & Module 2 checkpoint | Performance Analyzer, DAX Studio and VertiPaq Analyzer basics; reducing cardinality; removing unused columns; 25-question quiz | Optimise a slow report and record the before / after timings | 2 | Not Started
17 | 17 | 2026-10-13 | 2026-10-13 | 3. Visualisations | Choosing the right visual | Best-fit visual by data relationship: clustered bar/column (comparison), line (trend over time), stacked bar or treemap (part-to-whole), scatter (correlation), waterfall (variance/bridge), sorted bar (ranking), card/KPI (single value), table/matrix (detail), filled or bubble map (geography) | Build one visual for each relationship type | 2 | Not Started
18 | 18 | 2026-10-14 | 2026-10-14 | 3. Visualisations | Report design & accessibility | Page layout, themes and JSON themes, alignment and consistency, mobile layout, alt text, tab order, colour contrast, titles | Design a three-page report with a custom theme | 2 | Not Started
19 | 19 | 2026-10-15 | 2026-10-15 | 3. Visualisations | Interactivity & navigation | Slicers and synced slicers; filters pane (visual / page / report); edit interactions; drill-down and drillthrough; tooltip pages; bookmarks, buttons, selection pane | Build a navigation menu with drillthrough | 2 | Not Started
20 | 20 | 2026-10-16 | 2026-10-16 | 3. Visualisations | Conditional formatting & analytics | Conditional formatting, reference lines, analytics pane, forecasting, Top N filters, error bars, AppSource custom visuals | Highlight outliers and add a forecast | 2 | Not Started
21 | 21 | 2026-10-19 | 2026-10-19 | 3. Visualisations | AI visuals & insights | Key influencers, decomposition tree, Q&A, smart narrative, anomaly detection, Copilot (if licensed); paginated reports overview | Use two AI visuals to explain a KPI change | 2 | Not Started
22 | 22 | 2026-10-20 | 2026-10-20 | 3. Visualisations | Power BI Service for reports | Publishing, workspaces, dashboards vs reports, pinning tiles, alerts, subscriptions, Analyze in Excel, exporting | Publish a report, build a dashboard and set an alert | 2 | Not Started
23 | 23 | 2026-10-21 | 2026-10-21 | 3. Visualisations | Module 3 checkpoint | Review of the whole domain; 20-question quiz | Full executive dashboard from design to publish | 2 | Not Started
24 | 24 | 2026-10-22 | 2026-10-22 | 4. Maintenance & Security | Workspaces, roles & licensing | Workspace roles (Admin, Member, Contributor, Viewer); apps and sharing; Free, Pro, Premium Per User and capacity licences | Create a workspace, assign roles, publish an app | 2 | Not Started
25 | 25 | 2026-10-23 | 2026-10-23 | 4. Maintenance & Security | Datasets, refresh & lifecycle | Scheduled refresh; personal vs standard gateways; incremental refresh; endorsement (promoted / certified); lineage view and impact analysis; deployment pipelines overview | Set up a scheduled refresh and review lineage | 2 | Not Started
26 | 26 | 2026-10-26 | 2026-10-26 | 4. Maintenance & Security | Security & governance | Row-level security (static and dynamic with USERPRINCIPALNAME); object-level security; View as testing; sensitivity labels; build permissions | Implement dynamic RLS and test it | 2 | Not Started
27 | 27 | 2026-10-27 | 2026-10-27 | 4. Maintenance & Security | Module 4 checkpoint | Review of the whole domain; 20-question quiz | End-to-end: RLS, app and refresh settings | 2 | Not Started
28 | 28 | 2026-10-28 | 2026-10-28 | 5. Mock Exams & Revision | Full mock exam 1 | Microsoft Learn free practice assessment, timed at about 100 minutes; review every wrong answer (optional certification prep) | Timed mock, then log wrong answers in the Notes column | 2 | Not Started
29 | 29 | 2026-10-29 | 2026-10-29 | 5. Mock Exams & Revision | Weak-area remediation | Redo labs and questions for the two weakest domains; timed DAX drills; case-study style questions | Targeted labs on weakest areas | 2 | Not Started
30 | 30 | 2026-10-30 | 2026-10-30 | 5. Mock Exams & Revision | Full mock exam 2 & exam strategy | Second timed mock; time management and flagging questions; final review of notes | Timed mock and final notes review | 2 | Not Started
Total | [7 empty] | 60 | 0 / 30 | 0
Formulas:
Date = IFERROR(INDEX('Schedule Planner'!$Q5:Q504,MATCH([Training Day #],'Schedule Planner'!$S5:S504,0)),"Set training days")
Day = IF(ISNUMBER([Date]),[Date],"")

## Assessment Log
Assessment Log
Enter Date and Score. % and status calculate automatically. Max Score values are suggested defaults; edit them to match your actual quizzes. The grey italic row is an example only.
Target % | 70% | Rough working target (assumption). PL-300 is scored out of 1000 with 700 to pass, so this is not an exact conversion.
Tier | Checkpoint | Session # | Date | Score | Max Score | % Score | Status vs Target | Weak Areas / Notes
Example | Example: Tier 2 Module 1 quiz (ignore or delete) | 3 | 2026-10-01 | 8 | 10 | 80% | On track | Merge join types
Tier 1 | End-of-course knowledge check | 4 |  |  | 10
Tier 2 | Module 1 checkpoint quiz: data preparation | 3 |  |  | 10
Tier 2 | Module 2 checkpoint quiz: model and DAX | 7 |  |  | 15
Tier 2 | Module 3 checkpoint quiz: visualisations | 11 |  |  | 15
Tier 2 | Capstone report review (rubric score) | 12 |  |  | 20
Tier 3 | Module 1 quiz: Data Connect & Preparation | 7 |  |  | 20
Tier 3 | Module 2 quiz: Data Model & DAX | 16 |  |  | 25
Tier 3 | Module 3 quiz: Visualisations | 23 |  |  | 20
Tier 3 | Module 4 quiz: Maintenance & Security | 27 |  |  | 20
Tier 3 | Full mock exam 1 (optional) | 28
Tier 3 | Full mock exam 2 (optional) | 30